## Porter Pace Men's Shelter
Area/Barrier | Barrier Type/ Description | Strategy for Removal | Status/ Actions | Person/Team Responsible | Deadline
Dining Rooms | Hand Wash Sink, Coffee Maker (children out of reach), Bowls, Plates, Utensils | Change the current table height to accommodate, update the sink height |  | Housing York Inc | 2025
Accessible Phones: Payphones and Desk Phones | Phones are not accessible for those who are hard of hearing or deaf | Work with Canadian Hearing Society when/if needed | To implement during future retrofit. Research has been completed, a relationship has been made Canadian Hearing Society. | Human Resources | 2025
Alarm Panel | Height on wall | Ensure that the panel is accessible to all. Look into a standard height for this. Look into getting a manipulation stick. Wait until Built Environment legislation is set where it may outline potential height requirements |  | Housing York Inc | 2025
Everywhere | Doors do not have wheelchair button open | Install as necessary | To implement during future retrofit | Housing York Inc | 2025
Doorways | Width | Wait until Built Environment legislation is set where it may outline potential width requirements | To implement during future retrofit | Housing York Inc | 2025
Kitchens | Sinks, Counters/Microwave are not at an accessible height. | Add/change current design for enhance accessibility for staff and client areas if/when refurbishment occurs. Service counters: Standards don't t list a specific height requirement, it does speak of accommodating ‘mobility aids’ which could be of varying heights. Other jurisdictions have listed a range of heights for the top of the counters (ranging from 880-915mm). In speaking with a representative from the gov’t, at this time, there is no specific height requirement. The Accessible Built Environments regulations will address access into and within buildings and such regulations will be harmonized with the Ontario Building Code. | To confirm legislated height requirements and implement during future retrofit | Housing York Inc | 2025
Rest Rooms/Bedrooms | No push buttons, no brail | Button and brail need to be added. Property Manager will look into the cost of a Braille sign. Buttons will be taken into consideration during a refurbishment. | To implement during future retrofit | Housing York Inc | 2025
Donation rooms and pantries have no acessible access | Currently no way for wheelchair to access this |  | To implement during future retrofit | Housing York Inc | 2025
Ramps at the side of the building North Exit | No ramp | Potential install of a ramp, pending space | To implement during future retrofit | Housing York Inc | 2025