## Integrated Standards
Integrated Accessibility Standards
Standard | Requirement | Process | Responsibly | Date to be completed | Status
ALL | Accessibility Policies | Policies are in place and are included in the HR Policy Manual. These policies can be made avaialble to anyone and be offered in accessible format if requested. A Statement of Committeement has been written and is included in the policy. | Senior Leadership | 2014-01-01 | Complete
ALL | Accessibility Plans Establish, implement, maintain and document a multi-year plan | Blue Door will create and maintain a multi-year accessibility plan. | Senior Leadership | 2014-01-01 | Complete with on going review
ALL | Training Employees and volunteers Board Members and Directors Others who provide goods, services or facilities on behalf of the organization | Blue Door will provide training to employees, volunteers and other staff members on Ontario’s accessibility laws and on the Human Rights Code as it relates to people with disabilities. Training will be provided in a way that best suits the duties of employees, volunteers and other staff members. | Senior Leadership | 2015-01-01 | Complete with on going review
ALL | Feedback Process | Feedback is welcomed and appreciated as it may identify areas that require change and it encourages continuous service improvements. Staff, stakeholders, board members, volunteers, guests, community partners and clients of Blue Door may request a feedback form at any time. | Senior Leadership | 2015-01-01 | Complete
IT & C | Accessible Formats and Communication support | Blue Door will provide or arrange for the provision of accessible formats and communication supports for persons with disabilities within 7 - 10 bueiness days and at no additional cost to the individual. Blue Door will take into account the person’s accessibility needs when customizing individual requests. At this point in time BDS does not have any unconvertable information. | Senior Leadership | 2016-01-01 | Complete with on going review
Employ | Posting Requirements | A note stating "In case of emergency please contact reception. If you require emergency information or if you require accommodation please let reception know upon arrival and sign in." will be included on the "Visitor's Log In" forms at reception and all program entrances. | Senior Leadership | 2014-01-01 | Complete
Employ | Recruitment: Notification about available policies and accommodation for applicants with disabilities Provide suitable accommodation that takes into account the applicant's accessibility needs due to diability | Blue Door must notify employees and the public about the availability of accommodation for job applicants who have disabilities. Applicants must be informed that these accommodations are available, upon request, for the interview process and other candidate selection methods. Blue Door must notify the successful applicant of their policies and supports for accommodating people with disabilities. | Senior Leadership | 2014-01-01 | Complete
Employ | Supports and accessible formats and communication supports for employees: Informaiton to perform their job. Information that is generally available to employees in the workplaceInforming | Upon request if an employee with a disability requests it, Blue Door will arrange for the provision of accessible formats and communication supports. | Senior Leadership | As needed | Complete with on going review
Employ | Workplace Emergency Response information | Individualized emergency response information for staff with disabilities: - Get individuals consent, then share this information with anyone designated to help them in an emergency; don’t share details of the employee’s disability, just what kind of help they need. - Review the emergency response information when: - the employee changes work locations - you review the employee’s overall accommodation needs - you review your organization’s emergency response policies. - Disabilities can be temporary or permanent, and “employee” includes paid staff, but not volunteers or unpaid staff -Upon request Blue Door will accommodate requests up to the point of undue hardship | Senior Leadership | 2012-01-01 | Complete
Employ | Documented individual accomodation plans | Blue Door must also develop and have in place written processes for documenting individual accommodation plans for employees with disabilities | Senior Leadership | on going | on going
Employ | Career Development and Advancement and Performance Management | Any department within Blue Door that utilizes performance management tools, or provides career development and advancement to their employees, must respect the accessibility needs of their employees with disabilities when developing these processes. Every department within Blue Door will provide a tailored workplace emergency response plan or information for employees with disabilities, if their disability makes it necessary. | Senior Leadership | 2016-01-01 | Complete with on going review
Employ | Return to work Process and Redeployment | Blue Door will develop and have return to work processes in place for employees who are absent from work due to a disability—and require disability-related accommodations in order to return to work. Blue Door will need to document these processes. The return to work process must include an outline of the steps Blue Door will take to facilitate the employee’s return to work and use documented individual accommodation plans and will be based on the list of modified duties Blue Door is able to offer. | Senior Leadership | 2016-01-01 | Complete with on going review
IT & C | Accessible websites and web content | Blue Door will provide or arrange for the provision of accessible formats and communication supports for persons with disabilities in a timely manner and at no additional cost to the individual. Blue Door will take into account the person’s accessibility needs when customizing individual requests. All departments governed by Blue Door will make its web content conform to the Web Content Accessibility Guidelines (WCAG) 2.0 at Level AA by the end of 2021. Web content includes any information which resides on an internet or intranet web site. | Senior Leadership | 2021-01-01 | Complete with on going review